## API Issue list
API | Pass/Fail | Issue | Related Party | Priority | SOK Comments | Zodiac Comments | 15-JUNE MEETING SOK/ZODIAC
v1/bookings/{{bookingNbr}}@{{operator}} | Pass | #. Add Create user id/date, last update user id/date | ZODIAC | Medium
v1/vessel-visits/{{vesselVisitCode}} | Pass | # Add cut off time object | ZODIAC | Medium |  | Could be post day 1.
v1/bookings/non-reefers/register | Pass | #. No validation on visit status(it allows creating new booking after vessel depared. | SOK | High | Done | It's controlled by VAS.
| Pass | #. No validation pickupValidityDate/receiveValidityDate. They can be past time. | SOK | High | Done | VAS has validation for this.
| Pass | #. no validation on commodityCode/commodityDescription(but VAS has a dropdown list which is retrieved from Zodiac) | SOK | Low | Done | It's controlled by VAS.
| Pass | #. Allowed noEmptyReturn/noFullIn with wrong value instead of Y/N(it's controlled by VAS) | SOK | Low | Done | It's controlled by VAS.
| Pass | #. Allowed more than 3 trucking companies(it's controlled by VAS) | SOK | Medium | Done | It's controlled by VAS.
| Pass | *. Shipper need to support 300 characters | ZODIAC | Low |  | Review after go-live
v1/bookings/{{bookingNbr}}@{{operator}}/update-information | Pass | #. No validation on visit status(it allows creating new booking after vessel depared, but it's controlled by VAS) | SOK | Medium | Done | It's controlled by VAS.
| Pass | #. Allowed to update non-reefer container type for reefer booking, or vice versa. It shouldn't be allowed.(It's controlled by VAS) | SOK | Medium | Done | It's controlled by VAS.
| Pass | #. Allowed to update ventilation/vetilationUom/humidity/temperaturature/temperatureUom for non-reefer booking | SOK | Medium | Done
| Pass | #. Allowed to update everything even after container transaction but it shouln't(it's controlled by VAS) | SOK | Medium | ?? | It's controlled by VAS.
| Pass | *. Cannot replace container type. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9183251
v1/bookings/{{bookingNbr}}@{{operator}}/nominate | Fail | *. Allowed nominating IM Full container to pickup mission when operator, container type are matched. It must allow only ST Empty container only. | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9181916
v1/commodities | Fail | *. Defined a new billing class for Harard to depend on through VAS, for future we shall have a column for hazards.(we can set a billing commodity type for Hazard) | ZODIAC | Showstopper |  | Waiting for Hazardeous commodity code list from SOK | SOK will provied early next week
v1/bol/create | Fail | #. Allow duplicate seal number under the same shipping line(it's controlled by MTS) | SOK | Medium | ?? | It's controlled by MTS.
| Fail | #. SOK IT may user userDefinedCode1 for saving ACID. | SOK | Medium | ??
| Fail | #. markAndNbr need to be mandatory for CFS stripping(it's controlled by MTS) | SOK | Medium | ?? | It's controlled by MTS.
| Fail | *. the Length of consignee, shipper, notifier should be 300 chahracters. | ZODIAC | Low |  | https://support.zodiacportsolutions.com/issues/9181954
| Fail | *. Not allowed undefined commodity code. It would be better if Zoidac can provide an API to register commodity code so it can be resolved by the MTS intermediate application immediatly. If it's not possible, any workaround need to be provided. Discussion in progress." | ZODIAC | Showstopper |  | Ticket pending
v1/bol/search | Fail | *. Liner Code can be added by "lineCode", data segregation is working fine but SOK IT to get "lineCode" for their own purpose. Action Item: add "lineCode" field to result of v1/bol/{{bolNbr}}@{{vesselVisitCode}}, v1/bol/search. | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9181947
v1/bol/{{bolNbr}}@{{vesselVisitCode}} | Fail | *. Liner Code can be added by ""lineCode"", data segregation is working fine but SOK IT to get ""lineCode"" for their own purpose. Action Item: add ""lineCode"" field to result of v1/bol/{{bolNbr}}@{{vesselVisitCode}}, v1/bol/search. | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9181947
| Fail | #. refCntrNbr is not returned by v1/bol/{{bolNbr}}@{{vesselVisitCode}}. It should be. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9181955"
v1/bol/{{bolNbr}}@{{vesselVisitCode}}/set-demurrage | Pass | #. Allowed updating demurrage date without selecting containers. it updates all the conatiner's demurrage date if there's no container selected (it's controlled by VAS) | SOK | High | Done | It's controlled by VAS.
| Pass | #. Demurrage date can be set with past date (it's controlled by VAS) | SOK | High | Done | It's controlled by VAS.
| Pass | #. if containers are delegated a trucking company by set-demurrage and shippingline wants to change the delegation, they needs to cancel-delegation and delegate again to another trucking company (it's controlled by VAS) | SOK | High | Done | It's controlled by VAS.
| Pass | *. Gate should allow delivering IM Full container until Demurrage date + 1 08:00(checking gate validation logic) | ZODIAC | Medium |  | Need to discuss with Dev
v2/cargo-service-requests/create-stripping-request | Pass | *. TAX ID should be captured from BOL. | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183157 Need to discuss with SOK
| Pass | *. Record customer name(Free text) and display it in the Invoice -> | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183161
v2/equipment/{{equipmentNbr}}/release-for-planning | Pass | #. Allow updating not existing OutVisit(it's controlled by VAS) | SOK | Medium | ?? | It's controlled by VAS.
| Pass | #. Allow updating without OutVisit(it's controlled by VAS) | SOK | Medium | ?? | It's controlled by VAS.
v2/equipment/registry/{{eqpNbr}}/update | Pass | #. No validation on container length while registering a new container | SOK | High | Done
v1/bookings/search | Pass | #. in createDate search criteria, it accepts if from date is later than to date(It's controlled by VAS) | SOK | Low | ?? | It's controlled by VAS.
v1/bookings/reefers/register | Pass | # temperature/temperatureUom should be mandatory(it's controlled by VAS) | SOK | High | Done | It's controlled by VAS.
v1/pti-requests/create | Fail | * "humidity" field exists but it seems not saved, there's no field in UI or v1/pti-requests/{{requestNbr}} -> | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9182248 Same as row 57
v1/temperature-config-requests/create | Pass | #. TMP_REEF hold needs to be applied to requested hold(It's controlled by VAS) | SOK | High | Done | It's controlled by VAS.
v2/cargo-service-requests/create-stripping-request | Pass | *. Any API for update/cacnel CFS request?(Showstopper) | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9183158 UI can be used to cancel request. Can't consider as showstopper
v2/equipment/{{equipmentNbr}}/update | Pass | #. Stop allowing updating examinationTime if a container's loc=I. It should allow it only for containers in yard. | ZODIAC | High |  | SOK can add validation in middleware | On ground, custom already doesn't update examinationtime if container isn't in yard. SOK will check internally.
| Pass | * examinationTime is visible only on XRAY_SCAN_TM.TMS_CNTR_GRP1. | ZODIAC | High |  | It will use UDT, under discussion with dev
| Pass | *. [NICE change] MGM copying to VGM should be for EX only. VGM mustn't be overwritten by MGM for other SS. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9183163
| Pass | #. txSuffix should be SOK(it's controlled by VAS) | SOK | Medium | Done | It's controlled by VAS.
| Pass | #. Sokhna to check on the billing event for XRAY, If it's applied so we will complete the billing event. If not we will register first the billing event and complete it after. | SOK | High | ??
v2/equipment/create | Pass | #. No validation on container length while registering a new container(it's controlled by VAS) | SOK | Medium | Done | It's controlled by VAS.
v1/truck-visits/appointments/timeslot?show-available-quota-only=Y | Fail | *. It returnes only for current date. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9183165
v1/truck-visits/appointments/create | Fail | *. License Plate is not associated with Truckng Company is returned when a truck is not under the appointment trucking company. This validation should be turned off. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9182191
v1/truck-visits/appointments/create | Fail | *. Allow creating an appintment with inactive/suspended truck. I must not be allowed. | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9182210
v1/truck-visits/appointments/{{apptNbr}}/update | Fail | *. "Event Type: not supported." is returned when user tried to make an appointment with 2 empty pickup or 2 empty receiving. | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9183253
v1/bookings/{{bookingNbr}}@{{operator}}/delegate | Fail | *. Once trucker A,B,C is onriginally delegated by shipping line, then A delegated trucker D. In this case, D is showing in truckingCompanies on the result v1/bookings/{{bookingNbr}}@{{operator}}, A is disappered. But it has to show A only, it shouln't contain truckers who are delegated by trucker. -> need more clarification. -. in above case, still tucker A,B,C,D are showing in delegationList. | ZODIAC | Showstopper |  | Need to discuss with SOK. | SOK will validate against aray "delegatefroCompanyCode" Need to be checked by SOK
v1/billings/quotations/quote-by-bol | Pass | *. [FLDL] Created at the first quotation successfully with all registered serives on the containers. After that, if user try to call the same API, it created another quotation with admin fees only(Customer service, Trucerk services and Admin fee). But it shouldn't if there's no outstanding charge on main items. | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183693
v1/billings/quotations/quote-by-bol | Pass | *. [FLDL] It shouldn't allow creating supplementary invoice without main invoice. | ZODIAC | High |  | Whenever invoice is generated first time its always main invoice and later on its supplementary invoice | SOK will check the suggested logic of searching an invoce if its created before by using an API, "/data/dataviews/invoiceHeader"
v1/billings/quotations/{quotationNbr}/generate-print | Fail | *. "Invalid PDF response or error in report service."" is returned even the quotation is already created. | ZODIAC | N/A |  | Item no more needed | Item no more needed
v1/export-certificates/create | Fail | *. Failed with the error message "Failed to create quotation: [ORA-01403: no data found\nORA-06512: at \"EBS_OWNER.EBS$QUOTATION\", line 252\nORA-06512: at line 1]" | ZODIAC | Showstopper |  | This is already fixed in SOKZQ
v1/pti-requests/{{requestNbr}}/assign-reefers | Fail | #. Allow assigning a container to multiple PTI Reuqest (it's controlled by VAS) | SOK | Medium | ?? | It's controlled by VAS.
v1/pti-requests/{{requestNbr}}/assign-reefers | Fail | #. Allow assigning CMA container to MSC PTI request, it mustn't (it's controlled by VAS) | SOK | Medium | ?? | It's controlled by VAS.
v1/pti-requests/{{requestNbr}}/assign-reefers | Fail | *. Need to allow containers until the request has numbers of containers not failed(=success or not inspected yet) up to origianl requested quantity on DISPATCHED state. | SOK | High | ?? | https://support.zodiacportsolutions.com/issues/9182292
v1/service-requests/{{requestNbr}} | Fail | * "humidity" field exists but it seems not saved, there's no field in UI or v1/pti-requests/{{requestNbr}} | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9182248
v1/rail-visits/{{railVisitCode}}/update | Pass | *. all the fields need to be optional -> We already minimized the mandatory fields as of system limit. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9182206 Need to discuss with SOK. ETA is mandatory
v2/equipment/weigh | Pass | #. Overweight pre-decision default value should be REJECT(VAS need to send REJECT by default when it creates appointment) | SOK | Medium | Done | It's controlled by VAS.
v1/truck-visits/weigh | Pass | #. It returns "eqpNbrs is mandatory.", it better to be optional. | ZODIAC | Medium |  | Need to discuss with SOK. | Zodiac doenst support updating of Truck Tare weight. SOK will update TK Tare weight in WMA. "EqpNbrs" will remain mandatory
v1/truck-visits/appointments/validate | Pass | #. If gate validation failed, WMA need to call /truck-visits/proceed-stage to PRE_INGATE to trigger validation logic again after resolve the validation error. | SOK | Medium | Done
v1/truck-visits/proceed-stage | Fail | * To proceed INGATE, it doesn't validate OCR info in request body | ZODIAC | Showstopper |  | https://support.zodiacportsolutions.com/issues/9182066
v1/billing-events/equipment/register | Pass | #. ML_CNTR;GOEIC_CNTA;NAFSA_CNTR isn't supported | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9183223
v1/billing-events/equipment/complete | Pass | *. LAB / QTY user eventDetails shouldn't be mandatory even for GOEIC and NAFSA. | ZODIAC | Medium |  | https://support.zodiacportsolutions.com/issues/9183223
v1/equipment/batch-apply-hold | Pass | #. Return succes message even the hold is already applied to the container | ZODIAC | Low |  | Review after go-live
v1/equipment/batch-remove-hold | Pass | #. Return succes message even the hold is not applied to the container | ZODIAC | Low |  | Review after go-live
eService(Storage - Create Quotation) v1/billings/quotations/quote-by-bol (with "billToCode": "GP001") | Pass | *. Delivery Date is mission(pay thru date). | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183681 Need to be fixed at API level
eService(Storage - Create Quotation) v1/billings/quotations/quote-by-bol (with "billToCode": "GP001") | Pass | *. taxId is missing on both request/response. taxId on request should update the quotation/invoice's tax id only, shouldn't reflect BOL's | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183681
eService(Storage - Create Quotation) v1/billings/quotations/quote-by-bol (with "billToCode": "GP001") | Pass | *. On E-Service, there're 2 options for container storage invoice - Normal / With X-RAY. with X-Ray should add one more X-Ray charge for the future. | ZODIAC | High |  | Need to discuss with SOK | As of now Zodiac doesn't support advance service charges untill its registered. SOK will discuss internally for possiblities
eService(Storage - Create Quotation) v1/billings/quotations/quote-by-bol (with "billToCode": "GP001") | Pass | *. [Release Charge] is missing. This is becuase of missing billing service, should be applied automatically on every import containers. | ZODIAC | High |  | https://support.zodiacportsolutions.com/issues/9183681
eService(Storage - payment) http://ssokzu001app:10003/WEBServices/WSChargeCalculation.asmx?op=RegisterPaymentByQuotationNo External API: TBD | Pass | *. [New Requirement] Upon payment online, Zodiac should record the invoice is paid online, and by which credit card type. This is required to let Oracle Fusion add bank charge which needs to be paid by SOK to the credit card company. | ZODIAC | High |  | [New Requirement] | Not supported by Zodiac and wasn't mentioned in requirement as well. SOK will revisit the requirement
v1/billing-events/trucks/register | Fail | *. "Object reference not set to an instance of an object." error returned for SAFETYVIO_TK with active gate transaction LP. | ZODIAC | Showstopper |  | This is already fixed in SOKZQ
RESPONSIBLE | PRIORITY | COUNT
ZODIAC | Low | 4
| Medium | 13
| High | 13 | Needed for Go-Live |  |  |  | ASSIGN | DELEGATE
| Showstopper | 11 | Needed for Go-Live |  |  | SL | A | D | XXXX123456
SOK | Low | 3 |  |  |  |  | B
| Medium | 16 |  |  |  |  | C
| High | 10
| Showstopper | 0
41
29

## TEST thru VAS UI 01-06
SR. # | SCENARIO | SOURCE | STATUS | DATE | TESTING DATA | ISSUE
1 | Shipping Line upload Dray-In list | VAS | Passed | 2023-06-01 | MSCU0531211
2 | Shipping Line upload Dray-Off list | VAS | Passed | 2023-06-01 | CONT3005001 | - V: Require to display notification on VAS
3 | Create appointment for Dray-In | VAS | Passed | 2023-06-01 | 060101 / MSCU0531211 Appointment Created Successfully - 158395465 | - V: Require to send null for BOL, Booking and OperatorCode
4 | Create appointment for Dray-Off | VAS | Passed | 2023-06-01 | 060102 / CONT3005001 Appointment Created Successfully - 158396615 | - V: Require to send null for BOL, Booking and OperatorCode
5 | Create appointment for 2x20' EX + 1x20' DM + 1x20' DI | VAS | Passed | 2023-06-01 | 060103 / MSCU0601201,MSCU0601202+MRKU7170430+GED for MSC310520 Appointment Created Successfully - 158408560 (for the first container) Appointment Updated Successfully - 158408560 (for the second container) Appointment Updated Successfully - 158408560 (for the third Import container) Appointment Updated Successfully - 158408560 (for the forth Empty container) | - V: WMA need to display the first receive transactions then on the outgate it should display the remaining delivery transactions. - V: WMA should in this case print 4 EIR tickets for the whole visit.
6 | Create appointment for 2x20' EX (One with X-Ray, One with ML) | VAS | Failed | 2023-06-01 | 060104 / MSCU0601203,MSCU0601204 Appointment Created Successfully - 158409326 (for the first container) Appointment Updated Successfully - 158409326 (for the second container) | - Z: Need to check why the XRAY hold was not applied on the XRAY container.
7 | Apply No Empty Return on BOL | VAS | Passed | 2023-06-01 | Hold applied successfully for all containers under BOL | -V: Error and notification messages should be display as pop up the same like other pages.
8 | Apply No Full Deliver on BOL | VAS | Passed | 2023-06-01 | Hold applied for all containes including the containers which already in-gated
9 | Create appointment for 1 DI (20 or 40) based on point 8 | VAS | Passed | 2023-06-01 | Transaction could be created with
10 | Create appointment for 1 RM (based on IM container in point 9) | VAS | Failed | 2023-06-01 | Appointment Created Successfully - 158401862 | - Z: No validation applied on creating appointment for hold containers. - V: Validation should be applied on VAS as per ZODIAC advise (They do not have validation on Holds on creating appointment)
11 | Apply No Full-In, No Empty-Out on booking | VAS | Passed | 2023-06-01 | We could not set No Full In restriction for booking MSC310520, but we were able to set the No Empty Out restriction We were able to set No Full In restriction for booking BOOK0106-1
12 | Create appointment for 1 RE (based on booking in point 11) | VAS | Passed | 2023-06-01 | 060105 / BOOK0106-1/ MSCU0106401 Passed as we couldn't create the transaction due to this restriction.
13 | Create appointment for 1 DM (based on booking in point 11) | VAS | Passed | 2023-06-01 | 060106 / GED for MSC310520 Passed as we couldn't create the transaction due to this restriction.
14 | Request container for Inspection (MTS) | MTS | Passed | 2023-06-01 | Request has been updated for inspection to PONU1744698 and MRKU0522734 | - Z: Zodiac to check the warning of updating examination time for DG containers.
15 | Ground container to IA | ZODIAC | Passed | 2023-06-01 | PONU1744698 and MRKU0522734 were grounded successfully
16 | Receive container in-time | ZODIAC | Failed | 2023-06-01 | Failed to push the information automatically once the container grounded to IA. | - S: Check the connection between ZODIAC ZU server (10.105.100.52) and AZURE server (10.199.32.10). (Connectivity issue)
17 | Modifying Inspection time and Result | MTS | Passed | 2023-06-01 | Modified Successfully for PONU1744698 and MRKU0522734
18 | Complete Inspection billing event(=Back-Stac k Request) | MTS | Passed | 2023-06-02 | Completed successfully for PONU1744698 and MRKU0522734
19 | Back-Stack container | ZODIAC | Passed | 2023-06-02 | PONU1744698 and MRKU0522734 were bac-stacked successfully
20 | Receive container out-time | ZODIAC | Failed | 2023-06-02 | Failed to push the information automatically once the container back-stacked. | - S: Check the connection between ZODIAC ZU server (10.105.100.52) and AZURE server (10.199.32.10). (Connectivity issue)
21 | Invoice settlement "Supplementary Invoice" | VAS | Failed | 2023-06-02 | Failed to create quotation: [Container:MRKU0847030\nService: HANDLING SERVICE. Ambiguous terminal service (HANDLING SERVICE) defined for this transaction. RELEASE CONTAINER WITH CARGO 40' HANDLING SERVICE TS FULL 40'\n] Failed to create quotation: [Container:MRKU0847030\nService: STORAGE BEFORE INSPECTION. No terminal service (STORAGE BEFORE INSPECTION) defined for this transaction. Attributes: Inspection Type:Manual Inspection Only Size:40' Load Status:FCL Equipment Mode:Dangerous Category:Import. \n] Quotation created successfully for BOL 226123287 | - Z: Zodiac to check the error in creating the quotation due to missing terminal services. -> this is due to missing billing services. need to update the contract properly. - Z: Zodiac to check why the quotation is keep created as long as there's no services to be calculated. - Z: Zodiac to check why the transhipment containers were included in BOL. - Z: Zodiac to provide a solution to create Invoices from quotation. - Z: Zodiac to check the schedule to minimize the interval (per hour instead of per day) * Can be used as a main invoice by providing general payer code (GP001) in the billToCode field.
22 | Update Customer Name | VAS | Passed | 2023-06-02 | Customer name updated for BOL 225443651 but it is not supporting arabic characters | - Z: Zodiac to check whether the application or the DB is supporting Arabic language or not.
23 | Trucker Invoices "Settelment" | VAS | Passed | 2023-06-02 | Settelment done for invoice I0000056
24 | Create VGM Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
25 | Create VAT Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
26 | Create Weight Fees Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
27 | Create Export XRAY Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
28 | Create Export Inspection Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
29 | Create Admin Fees Invoice | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
30 | Create Truck Safety Violation | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
31 | Create Truck Security Violation | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
32 | Create Damage Caused Invoices | VAS | Failed | 2023-06-02 |  | - Z: Not ready to be tested.
33 | Create Rail Visit | VAS | Passed | 2023-06-01 | Rail visit created for rail (0601(01))
34 | Create RE List for Rail | VAS | Failed | 2023-06-01 | RE List uploaded for 10 containers. MSCU0106402,MSCU0106403,MSCU0106404,MSCU0106405,MSCU0106406,MSCU0106407,MSCU0106408,MSCU0106409,MSCU0106410 | - Z: No validation on the number of discharged or the loaded containers. - Z: No validation on the assigned rail operator, as the container has been uploaded although they are assigned to Trucker OAO
35 | Create RM List for Rail | VAS | Failed | 2023-06-01 | RM List uploaded for 11 containers(But it should not been uploaded) MSCU0106411,MSCU0106412,MSCU0106413,MSCU0106414,MSCU0106415,MSCU0106416,MSCU0106417,MSCU0106418,MSCU0106419,MSCU0106420 | - Z: No validation on the number of discharged or the loaded containers. - Z: No validation on the assigned rail operator, as the container has been uploaded although they are assigned to Trucker OAO. - Z: Demurrage date is required and it should be validated from ZODIAC
36 | Create DI List for Rail | VAS | Failed | 2023-06-01 | DI List could not be uploaded | - Z: No validation on the number of discharged or the loaded containers. - Z: No validation on the assigned rail operator, as the container has been uploaded although they are assigned to Trucker OAO. - Z: Demurrage date is required and it should be validated from ZODIAC
37 | VGM Transaction | VAS | Passed | 2023-06-01 | VGM and DGM has been updated for container MSCU0106401 with 28700
38 | BOL Delegation | VAS | Failed | 2023-06-01 | Delegate Containers from BOL to AFT | - Z: Check why trucker cannot delegate any containers from BOL as he supposed to.
39 | Booking Delegation | VAS | Failed | 2023-06-01 | Delegate booking from OAO to AFT | -Z: Delegated truck should not be included in the trucker list for booking(OAO is the assigned trucker from MSC, and OAO just want to delegate the booking to AFT. OAO is the responsible party for booking transactions)
40 | Export Certificate | VAS | Failed | 2023-06-02 | Failed to create quotation: [ORA-01403: no data found ORA-06512: at "EBS_OWNER.EBS$QUOTATION", line 252 ORA-06512: at line 1]54060: Fail to create export certificate! | - Z: Zodiac to check why we cannot create an export certificate for trucker.

## LG TEST 02-06
SR. # | SCENARIO | STAGE | RESULT | MISSION | LG BOOK/CONSUME | TEST DATA | OUTPUT
1 | Create appointment for RE 1x20' (Appointment API) | VAS |  | Export Receive | Book LG for, 1. VGM admin fee 2. Truck Card 3. Truck Card Admin | Trucker : TKR01 License Plat : TKR060102 Container Number: CMAU0601202
2 | Gate-In container from point 1 (Equip. weighing API) | Main Gate (WB) |  | Export Receive | Book LG for, 1. VGM admin fee 2. VGM penalty fee 3. Container Overweight | Trucker : TKR01 License Plat : TKR060102 Container Number: CMAU0601202
3 | Gate-Out container from point 1 (Proceed API) | Out-Gate (WB) |  | Export Receive | Consume LG for, 1. Truck card fee 2. Truck card admin fee 3. Truck overstay charge 4. VGM admin fee 5. VGM fee (Conditional) 6. Truck weighing fee 7. Truck overweight | Trucker : TKR01 License Plat : TKR060102 Container Number: CMAU0601202
4 | Create appointment for DI 1x20' (Appointment API) | VAS |  | Import Delivery | Book LG for, 1. VAT (against weight in inventory) | 20'= HXXX1234560, HXXX1234561, HXXX1234564 40'= HXXX1234562, HXXX1234563
5 | Gate-In container from point 4 (Proceed API) | Main Gate (WB) |  | Import Delivery | No impact on LG
6 | Gate-Out container from point 4 (Truck weighing API) | Out-Gate (WB) |  | Import Delivery | Book LG for, 1. VAT fee (weight from WMA) 2. Truck weighing fee
7 | Gate-Out container from point 4 (Proceed API) | Out-Gate (WB) |  | Import Delivery | Consume LG for, 1. VAT fee (weight from WMA) 2. Truck weighing fee
8 | Create appointment for Dray-In receive 1x20' (Appointment API) | VAS |  | Dray-In Receive | Book LG for, 1. Truck Card 2. Truck Card Admin
9 | Gate-In container from point 8 (Truck weighing API) | Main Gate (WB) |  | Dray-In Receive | Book LG for, 1. Truck weighing fee
10 | Gate-Out container from point 8 (Proceed API) | Out-Gate (WB) |  | Dray-In Receive | Consume LG for, 1. Truck card fee 2. Truck card admin fee 3. Truck overstay charge 4. Truck weighing fee
11 | Create appointment for RM 1x20' (Appointment API) | VAS |  | Receive Empty | Book LG for, 1. Truck Card 2. Truck Card Admin
12 | Gate-Out container from point 11 (Proceed API) | Out-Gate (WB) |  | Receive Empty | Consume LG for, 1. Truck card fee 2. Truck card admin fee 3. Truck overstay charge
13 | Create appointment for DM 1x20' (Appointment API) | VAS |  | Deliver Empty | Book LG for, 1. Truck Card 2. Truck Card Admin
14 | Gate-Out container from point 13 (Proceed API) | Out-Gate (WB) |  | Deliver Empty | Consume LG for, 1. Truck card fee 2. Truck card admin fee 3. Truck overstay charge
15 | Create appointment for Dray-In Delivery 1x20' (Appointment API) | VAS |  | Dray-In Delviery | NUL
16 | Gate-Out container from point 15 (Truck weighing API) | Out-Gate (WB) |  | Dray-In Delviery | BookLG for, 1. Truck weighing fee
17 | Gate-Out container from point 15 (Proceed API) | Out-Gate (WB) |  | Dray-In Delviery | Consume LG, 1. Truck weighing fee
18 | Create appointment for Transit Delivery 1x20' (Appointment API) | VAS |  | Transit Delviery | Book LG for, 1. Truck Card 2. Truck Card Admin
19 | Gate-Out container from point 18 (Proceed API) | Out-Gate (WB) |  | Transit Delviery | Consume LG for, 1. Truck card fee 2. Truck card admin fee 3. Truck overstay charge

## VAS - API
No. | API | Position
1 | v1/auth/login | Login-Page
2 | v1/auth/logout | All-Pages
3 | v1/bookings/{{bookingNbr}}@{{operator}} | Any Page uses search button for bookings
4 | v1/vessel-visits/search | Any Page that allows user to select vessel
5 | v1/truck-companies?includeLicencePlate=false | Any Page that allows user to select trucker company
6 | v1/bookings/non-reefers/register | Booking creation page
7 | v1/bookings/{{bookingNbr}}@{{operator}}/update-information | Booking creation page ( Also reefers)
8 | v1/bookings/{{bookingNbr}}@{{operator}}/delete | Booking creation page ( Also reefers)
9 | v2/equipment/search | Any page that uses search for containers availability
10 | v2/equipment/{{requestId}}/polling | Any Page that uses search for container details via polling
11 | v2/equipment/container-types | Any page that requires selection of ISO code
12 | v1/imo-codes | Any page that requires selection of IMO code
13 | v1/commodities | Any page that requires selection of commodity code
14 | v1/package-types | Stuffing request creation page
15 | v1/bol/create | Stuffing request creation page & Customs
16 | v1/bol/search | Stuffing request creation page & any page requires searching for a booking
17 | v1/bol/{{bolNbr}}@{{vesselVisitCode}} | Search for a bol to show containers like in Demurrage page to get containers in a bol
18 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/set-demurrage | setting demurrage date page
19 | v2/cargo-service-requests/create-stripping-request | Stripping request page
20 | v2/equipment/{{equipmentNbr}}/release | Load list page & load list cut-off page
21 | v2/equipment/registry/{{eqpNbr}} | Add/Modify container page
22 | v2/equipment/registry/{{eqpNbr}}/update | Add/Modify container page
23 | v1/bookings/search | Any page that uses search button for bookings using special parameters
24 | v1/bookings/reefers/register | Reefer Booking creation page
25 | v1/pti-requests/{{requestNbr}} | PTI page
26 | v1/pti-requests/create | PTI page
27 | v1/temperature-config-requests/create | Temperature page in reefers
28 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/apply-hold | Used in any page that takes containers to apply hold on
29 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/remove-hold | Used in any page that takes containers to remove hold From
30 | v2/equipment/{{equipmentNbr}}/update | Transit list page & RE transaction ( basically any page that updates info of a container or lists) X-ray page to update examination time of a request and in WMA to update container info && update custom status
31 | v2/equipment/create | Empty & Export list page
32 | v2/equipment/delegate | Empty & Export list page
33 | v1/truck-visits/appointments/search | All transaction page
34 | v1/truck-visits/appointments/timeslot?show-available-quota-only=Y | All transaction page
35 | v1/operators/search | All transaction page & shipping line module
36 | v2/equipment/polling/${requestId} | All transaction page
37 | v1/truck-visits/appointments/create | All transaction page
38 | v1/truck-visits/appointments/{{apptNbr}}/update | All transaction page
39 | v1/truck-visits/appointments/{{apptNbr}}/cancel | Transaction inquiry page
40 | v1/truck-visits/appointments/{{apptNbr}} | Transaction inquiry page
41 | v1/bookings/{{bookingNbr}}@{{operator}}/delegate | Booking delegation page
42 | v1/bookings/{{bookingNbr}}@{{operator}}/cancel-delegate | Booking delegation page
43 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/delegate | BOL delegation page
44 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/cancel-delegate | BOL delegation page
45 | v1/billing-events/equipment/register | Used to add service ( inspection ) to a container
46 | v1/billings/quotations/quote-by-cntr | Trigger billing event related to overweight
47 | v1/truck-visits/appointments/{{apptNbr}}/print | Should be used to print appoitment data
48 | v1/billings/quotations/quote-by-bol | Create invoice page to trigger bol billing event
49 | v1/export-certificates/create | Export procedure page
50 | v1//truck-visits/get-truck-mission-summary | Planner module
51 | v1/service-requests/{{requestNbr}}/approve | Planner module - PTI page
52 | v1/service-requests/{{requestNbr}}/dispatch | Planner module - PTI page
53 | v1/pti-requests/{{requestNbr}}/assign-reefers | Planner module - PTI page
54 | v1/truck-companies/search | Trucker module
55 | v1/service-requests/{{requestNbr}}/complete | Technical module - Update temp - Update repair status
56 | v1/temperature-config-requests/{{requestNbr}} | Technical module - Update temperature
57 | v1/service-requests/{{requestNbr}} | Technical module - search for PTI requests
58 | v1/service-requests/create | Technical module - emergency PTI requests & Repair list page
59 | v1/service-requests/{{requestNbr}}/update | Technical module - emergency PTI requests
60 | v1/service-requests/{{requestNbr}}/update-operation-checklist | Technical module - Update PTI per request or per reefer
61 | v1/service-requests/search | Technical module - Update PTI per reefer
62 | v1/rail-visits/create | Rail module - train schedule
63 | v1/rail-visits/{{railVisitCode}}/update | Rail module - train schedule
64 | v1/rail-visits/{{railVisitCode}}/delete | Rail module - train schedule
65 | v1/rail-visits/{{railVisitCode}} | Rail module - train schedule
66 | v1/billing-events/equipment/complete | X-ray page to complete a request ( related to billing)
67 | v1/truck-visits/proceed-stage | Used in X-ray and WMA to procceed the stage
68 | v1/truck-visits/get-visit | Used in WMA to retrieve mission info the stage
69 | v2/equipment/weigh | Used in WMA for weighing of container.
70 | v1/truck-visits/weigh | Used in WMA for weighing of truck.
71 | v1/truck-visits/appointments/validate | Used in WMA to create a mission.
72 | LG Check | Used in every page that triggres a billing event to be deducted from trucker lg
73 | Load-List Search and modify API | Used in a page to search for uploaded load lists and ability to delete containers from load list
74 | Non-PTI requests | Used to create a non PTI - request
75 | Report / Load List recap API | Used to get a recap report for load-list
76 | Stripping & Stuffing Weighing Process | Used in WMA application to quantify the amount of packages used

## WMA
No. | API | Position
1 | v1/auth/login | Login-Page
2 | v1/truck-visits/get-visit | Weight
3 | v2/equipment/{{equipmentNbr}}/update | Weight
4 | v2/equipment/weigh | Weight
5 | v1/truck-visits/weigh | Weight
6 | v1/truck-visits/proceed-stage | Weight
7 | v2/equipment/registry/${values.CntrNbr} | Weight
8 | v1/equipment/container-types | Weight
9 | v1/data/dataviews/eqpActiveInventory | Weight
10 | https://vm-webportal-t.dpwsapps.com/WMA_API/save-RTGWeight | RTG Weighment

## CAMCO
No. | API | Position
1 | v1/auth/login | Backend login
2 | /v1/truck-visits/appointments/validate | OCR Validation
3 | v2/equipment/${container number}/update | UPDATE Container details (CAMCO’s TRUCK DATA TRANSACTION)
4 | /v1/truck-visits/proceed-stage | update the truck visit’s gate stage when the truck RFID is read on each stage

## MTS
No. | API | Position
1 | v1/auth/login | Backend login
2 | https://vm-webportal-t.dpwsapps.com/sokz_ws/api/sokz/vessel-visit | Zodiac will call restful API to push the vessel visit information when it is created
3 | https://vm-webportal-t.dpwsapps.com/sokz_ws/api/sokz/vessel-visit | Zodiac will call restful API to push the vessel visit information when it is updated
4 | v1/bol/create | BOL Creation
5 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/update
6 | v1/billing-events/equipment/register | Inspection Selection
7 | https://vm-webportal-t.dpwsapps.com/sokz_ws/api/sokz/container-info | Zodiac will call restful API to push the container information
8 | v2/equipment/${equipmentNbr}/update | Results update
9 | v1/billing-events/equipment/complete | Sample Labs (Invoicing)

## 2Fusion
No. | API | Position
1 | v1/auth/login | Login page
2 | v1/data/dataviews/invoiceHeader | Invoices
3 | v1/billings/invoices/{invoiceNbr} | Invoices
4 | v1/billing/invoices/settle-invoice | Receipts

## Customs Application
No. | API | Position
1 | v1/auth/login | Backend login
2 | v1/equipment/batch-apply-hold | Apply Hold
3 | v1/equipment/batch-remove-hold | Release Hold

## CustomRelease
No. | API | Position
1 | v1/auth/login | Backend login
2 | v1/bol/{{bolNbr}}@{{vesselVisitCode}}/remove-hold | Release Hold

## E-Services
No. | API | Position
1 | v1/auth/login | Backend login
2 | No API | Performa Invoice
3 | No API | Storage Invoice
4 | No API | BL Tracking
5 | No API | Inspection Inquiry
6 | No API | Vessel Schedule
7 | No API | Vessel on Berth