## Sheet1
Module | Pages Number | Estimated Development Working Days / man power = 2 | Content
Shipping Line | 36 | 18 | Export (Booking - Stuffing Bulk- Stuffing Break Bulk - Rehandle)
Import (Set Demurrage - Stripping Create - Striiping Search - Stripping Cancel)
Vessel (Upload Load List - Cancel Load List - Upload Cuttof Load List)
List (Empty List - Export List (upload - cancel)- Transit List - Dray in - Dray Off)
Requests (Add or Modifiy Container - Container Tracking - Xray - Manual inspection)
Refeer (Booking - Repair - PTI - Temperature)
Report (Booking Recap - Booking Tracking - Load List Recap)
Hold (No Empty Deliver - No Full Deliver)
Trucker | 24 | 15 | Transactions (RM - RI - RE - DM - DI - DE - Transaction Query - Cancel Transaction)
Appointment (Search)
Delegation (Booking - BOL)
Services (Import Inspectoin - Manual Inspection - X-Ray - Overweight)
Invoices (Search - Create - Export Procedure)
CFS Gate Pass (Search - create - Delete - print - print Request)
Rail | 6 | 5 | Visits(Create - Delete - Inquiry) - Lists (RE - RM - DI)
Planner | 3 |  | Assign Refeer - Approve PTI - Cancel Load List
Technical | 6 | 5 | PTI(Print Refeer - Apply PTI Request - Apply PTI Refeer) - Refeers (Booking - PTI - Temperature) - R&M (Create - Approve)
Cargo Owner | 1 |  | Register VGM
User Identity (reset and change password) | N/A | 5 | Admin Pages for user management
Total |  | 48