## Sheet1
No | Department Priority | Department Name | Request Name | Request Type | Request Priority | Start Date | End Date | Working Days | Department Start Date | Department End Date
| Design ERD, Create DB, Prepare Businss Logic for development, Design Front End Layout |  |  |  |  | 13/8/2023 | 2023-11-09 | 15
| User Management (Create, Add role, Authentication, Authorization,Lock, Unlock) |  |  |  |  | 2023-12-09 | 13/9/2023 | 2
1 | 5 | IT | Domain Account | old | 7 | 15/10/2023 | 15/10/2023 | 1 | 2023-10-10 | 31/10/2023
2 |  |  | Application User | old | 6 | 2023-10-10 | 2023-12-10 | 3
3 |  |  | DB User | new | 8 | 16/10/2023 | 16/10/2023 | 1
4 |  |  | DR Drill | new | 9 | 17/10/2023 | 18/10/2023 | 2
5 |  |  | Backup / Restore | new | 10 | 19/10/2023 | 22/10/2023 | 2
6 |  |  | IT Assets | new | 11 | 23/10/2023 | 23/10/2023 | 1
7 |  |  | Remote Access | new | 12
8 |  |  | Datacenter access | new | 13 | 24/10/2023 | 25/10/2023 | 2
9 |  |  | Backup Deposite | new | 14 | 26/10/2023 | 26/10/2023 | 1
|  |  | UAT |  |  | 29/10/2023 | 31/10/2023 | 3
10 | 11 | HR | Voucher | old | 25 | 21/11/2023 | 21/11/2023 | 1
|  |  | UAT |  |  | 22/11/2023 | 22/11/2023 | 1
11 | 6 | Security | CCTV | old | 15 | 2023-01-11 | 2023-02-11 | 2 | 1/11/223 | 2023-05-11
12 |  |  | AXIOM | old | 16
|  |  | UAT |  |  | 2023-05-11 | 2023-05-11 | 1
13 | 1 | Procurment | PO | old | 1 | 14/9/2023 | 21/9/2023 | 6 | 14/9/2023 | 24/9/2023
|  |  | UAT |  |  | 24/9/2023 | 24/9/2023 | 1
14 | 7 | Stores | Fuel oil invoice | new | 17 | 2023-06-11 | 2023-06-11 | 1 | 2023-06-11 | 2023-12-11
15 |  |  | PR | new | 18 | 2023-07-11 | 2023-07-11 | 1
16 |  |  | New Item | new | 19 | 2023-08-11 | 2023-08-11 | 1
17 |  |  | Manlift Reservation | new | 20 | 2023-09-11 | 2023-09-11 | 1
|  |  | UAT |  |  | 2023-12-11 | 2023-12-11 | 1
18 | 8 | Operation | Equipment Request (In concession area) | new | 21 | 13/11/2023 | 13/11/2023 | 1 | 13/11/2023 | 14/11/2023
19 |  |  | Equipment Request (Out concession area) | new | 22
|  |  | UAT |  |  | 14/11/2023 | 14/11/2023 | 1
20 | 9 | Engineering | MOC | new | 23 | 15/11/2023 | 15/11/2023 | 1 | 15/11/2023 | 16/11/2023
|  |  | UAT |  |  | 16/11/2023 | 16/11/2023 | 1
21 | 10 | Communication | Multimedia | new | 24 | 19/11/2023 | 19/11/2023 | 1 | 19/11/2023 | 20/11/2023
|  |  | UAT |  |  | 20/11/2023 | 20/11/2023 | 1
22 | 4 | Commercial | Customer Dicount | new | 5 | 2023-04-10 | 2023-08-10 | 2 | 2023-04-10 | 2023-09-10
|  |  | UAT |  |  | 2023-09-10 | 9/10/203 | 1
23 | 3 | Customer Service | Customer Refund | new | 4 | 2023-01-10 | 2023-02-10 | 2 | 2023-01-10 | 2023-03-10
|  |  | UAT |  |  | 2023-03-10 | 2023-03-10 | 1
24 | 2 | Admin | Car Request | old | 2 | 25/9/2023 | 26/9/2023 | 2 | 25/9/2023 | 27/9/2023
|  |  | Travel Desk | old | 3
25 |  |  | UAT |  |  | 27/9/2023 | 27/9/2023 | 1