## Sheet1
No | Point | Request | Category | Dev Comment | Due Date | Accountability
1 | Files cannot be downloaded in PO request ( This issues occurred many times and then it gets fixed without interference) | PO | Must Have | Will be chekced | 22/10 | Back & Front
2 | Remarks field are shown to user as null whenever they are empty | PO | Nice to have | Noted | 22/10 | Front
3 | Date format should be more be user friendly instead of 2023-10-20T12:39:00 | PO & Administration | Nice to have | Noted | 22/10 | Front
4 | Reviewer tab sometimes is shown to user as empty tab | PO | Should be Fixed | Will be chekced | 22/10 | Back & Front
5 | Reviewer can decline a request without entering any readable notes by entering a free space | PO & Administration | Should be Fixed | Noted | 22/10 | Back & Front
6 | When a reviewer declines a request , he can't find this request again as it vanishes from his inbox , and it's only available for the request creator | PO & Administration | Nice to have | Scope of Work | N/A | N/A
7 | The reviewer tab still shows assigned reviewers for the request even if the request is declined already. | PO & Administration | Nice to have | Scope of Work (As displaying the list of request reviewer is not depending on their actions) | 22/10 | N/A
8 | The reviewer tab shows request status as declined if the request has been declined and then updated , while it is showed in the inbox as pending | PO & Administration | Should be Fixed | Noted | 22/10 | Back
9 | The reviewer tab shows duplicated number of assigned reviewers if the request has been declined and then updated | PO & Administration | Should be Fixed | Noted | 22/10 | Back
10 | If a stage in a request is declined already , the reviewers tab still shows the subsequent stages as pending | Administration | Should be Fixed | We will make the default status equals 'None' instead of 'Pending' | 22/10 | Back & Front
11 | System allows duplication of requests as the user can insert the same request with the same data | PO & Administration | Should be Fixed | Scope of Work (Each request has a different ID and the end users didn't ask to apply unique constrain on any fields) | N/A | N/A
12 | When using the export to excel , the file downloaded has the name of table_data , which should be a descriptive name | PO & Administration | Nice to have | Noted | 22/10 | Front
13 | For travel desk and vehicle request the to date can be a date that is before the from date in all date fields | Travel Desk | Must Have | Noted | 22/10 | Front
14 | Luggage description should have a certain format to be descriptive as this a free text field and it's not descriptive | Vehicle Request | Nice to have | Noted | 22/10 | Front
15 | When a user approves a request that has multiple stages , the request is approved , but it still shows as pending because the cycle was not completed to the end , however it should show each user the request his approval | PO & Administration | Nice to have | Noted | 22/10 | Back
16 | Flight ticket from and to fields are defined as date while it should be date time | Travel Desk | Must Have | Noted | 22/10 | Front
17 | When an HOD creates Travel desk request or vehicle request , the request is assigned to him to be approved , which should be approved automatically | Administration | Must Have | Noted | 22/10 | Back
18 | When Administration HOD (Ahmed Zaki) creates a travel desk or vehicle request , the request gets automatically assigned to him and then approved automatically , but yet it shows another stage for him to approved and it's pending, However system doesn't allow him to approve it | Administration | Must Have | Noted | 22/10 | Back
19 | Can't update the user access for any user in the E-Document | IT Dashboard | Should be Fixed | Noted | 22/10 | Back
20 | Can't lock any user from the administration page | IT Dashboard | Should be Fixed | It's working normally now but basiclly All administration activities (Password Expiration, Password Change, Password Reset, Lock, Disable) for Employees that have LDAP should be handled basicly on Active Directory, Adminstiration Page is used for table based users which is not included in these PO and Adminitration Requests | N/A | N/A
21 | Any user can be updated to be the HOD even if this user doesn't belong to this department | IT Dashboard | Must Have | Noted | 22/10 | Back

## Sheet2
Transaction | Validation | status
DI | Check container holds (should be released and have no holds) | old
| Check container location (should be in yard) | old
| Validate BOL Demurage Date | old
DM | Validate Booking No Empty out | new
| Check the available containers with the selected ISO in SL pool | old
| Validate Booking Validity date | old
RE | Check Cut off time using eta | new
| Validate Booking No Empty out | new
| Validate Booking Validity date | old
RM | Check container location (shouldn't be in yard) | old
Dray Off | Check container shipping status (should = BT) | old
| Check container holds (should be released and have no holds) | old
Dray In | Check container shipping status (should = IM) | old